## Corrective Actions
Supplier Contract Compliance - Corrective Action Plan
Supplier | Issue | Required Action | Owner | Target Date | Est. Cost | Status
TechServices Inc | Missing liability clause | Add 12-month liability cap | Patricia Wilson | 2026-04-06 | 0 | In Progress
Global Logistics | Missing SLA definition | Negotiate SLA addendum | Patricia Wilson | 2026-04-21 | 5000 | Planned
Global Logistics | Inadequate confidentiality | Supplement confidentiality clause | Jennifer Smith | 2026-04-06 | 0 | In Progress
Quality Manufacturing | Non-compliant payment terms | Renegotiate payment terms | Patricia Wilson | 2026-05-06 | 10000 | Planned
Quality Manufacturing | Undefined quality standards | Add quality standards annex | Patricia Wilson | 2026-04-21 | 3000 | Planned
Consulting Group Ltd | Vague scope definition | Clarify scope of services | Patricia Wilson | 2026-04-06 | 0 | In Progress
Consulting Group Ltd | Ambiguous IP ownership | Establish clear IP terms | Jennifer Smith | 2026-04-21 | 2000 | Planned
Summary
Total Actions Required | 7
In Progress | 3
Planned | 4
Total Estimated Cost | 20000